## DETAILED
DETAILED ESTIMATE
CONSTRUCTION OF BRIDGE ACROSS PERIYAR VALLEY PARAVOOR BRANCH CANAL FOR UC COLLEGE,ALUVA(6M WIDE)
SL. | Specification | No. | L | W | H/D | M2 | Quantity | UNIT
1 | Demolishing the existing Cement Concrete layer on the sides manually/by mechanical means, including disposal of material within 50 metres lead as per the direction of engineer -in charge.
| Existing canal lining if any | 2 | 3 | 6.6 | 0.1 |  | 3.96 | M3
| Existing canal floor lining if any | 1 | 4.12 | 6.3 | 0.1 |  | 2.5956 | M3
| Total | [5 empty] | 6.5556 | M3
| Total quantity | [5 empty] | 6.5556 | M3
2 | Earthwork excavation by mechanical means(hydraulic excavator )/manual means for abutment construction upto 3.60m depth including disposal of excavated earth , lead upto 50m and lift upto 3.60m, disposed earth to be levelled and neatly dressed , all kinds of soil and waste.
| For abutmen and wing wall | 2 | 6.7 |  |  | 7.02 | 94.068 | M3
| Total | [5 empty] | 94.068 | M3
| Total quantity | [5 empty] | 94.068 | M3
3 | Random Rubble in Cement Mortar
| For abutment bottom | 2 | 2.6 | 6.7 | 0.3 |  | 5.226 | M3
| Total | [5 empty] | 5.226 | M3
| Total quantity | [5 empty] | 5.226 | M3
4a | Random Rubble - Dry packed
| For Abutment side | 6.3 |  |  |  | 1.05 | 6.615 | M3
| Total | [5 empty] | 6.615 | M3
| Total quantity | [5 empty] | 6.615 | M3
OR
4b | 20cm Block Work masnory in CM
| For Abutment side | 6.3 |  |  |  | 1.05 | 6.615 | M3
| Total | [5 empty] | 6.615 | M3
| Total quantity | [5 empty] | 6.615 | M3
5 | Plain Cement concrete lining for canal 1:2:4 finished with a floated coat of neat cement , including cement slurry etc using 20mm nominal size stone aggrerates.
| PCC for footing | 2 | 2.75 | 6.7 | 0.1 |  | 3.685 | M3
| PCC for retaining wall on sides | 1 | 9.9 | 0.4 | 0.1 |  | 0.396 | M3
| Total | [5 empty] | 4.081 | M3
| Total quantity | [5 empty] | 4.081 | M3
6 | Providing and laying in position of vibraed RCC M25 mis using 20mm nominal size coarse aggregates including shuttering and centering works,propping ,removal of formwork for foundations and footings
| Footing | 2 | 6.3 | 2.6 | 0.7 |  | 22.932 | M3
| Abutment | 2 | 6.3 | 0.7 | 2.15 |  | 18.963 | M3
| Bedblock | 2 | 6.3 | 0.55 | 0.3 |  | 2.079 | M3
| Kerb | 2 | 0.15 | 24.24 | 0.15 |  | 1.0908 | M3
| Handrail post | 16 | 0.15 | 0.15 | 1 |  | 0.36 | M3
| Side retaining wall(sloping along sides)3.43m hi | 1 | 9.9 | 0.2 | 2.058 |  | 4.0748 | M3
| Total | [5 empty] | 49.4996 | M3
| Total quantity | [5 empty] | 49.4996 | M3
7 | Providing and laying in position of Vibrated RCC mix M25 using 20mm nominal size coarse aggregates including shuttering & centering works,propping ,removal of formwork for slab, Beams
| BEAM | 3 | 6.77 | 0.5 | 0.55 |  | 5.5853 | M3
| SLAB | 1 | 6.77 | 6.3 | 0.2 |  | 8.5302 | M3
| Total | [5 empty] | 14.1154 | M3
| Total quantity | [5 empty] | 14.1154 | M3
8 | Providing and laying in position of Vibrated RCC mix M25 using 20mm nominal size coarse aggregates including shuttering &centering works,propping ,removal of formwork for slab.
| Approach Slab 1 |  |  |  | 0.15 | 13.66 | 2.049 | M3
| Approach Slab 1 |  |  |  | 0.15 | 18.21 | 2.7315 | M3
| Total | [5 empty] | 4.7805 | M3
| Total quantity | [5 empty] | 4.7805 | M3
9 | Providing and laying in position of vibrated RCC mix M25 using 20mm nominal size coarse aggregates laid in slope towards sides above the slab in a maximum size of 3x3 m grid.
| Wearing Coat Concrete - above slab |  | 6.75 | 6 | 0.1 |  | 4.05 | M3
| Wearing Coat Concrete - approach area |  |  |  | 0.1 | 13.66 | 1.366 | M3
| Wearing Coat Concrete - approach area |  |  |  | 0.1 | 18.21 | 1.821 | M3
| Total | [5 empty] | 7.237 | M3
| Total quantity | [5 empty] | 7.237 | M3
10 | Steel reinforcement for RCC work including straightening,cutting, bending,placing in position and binding all complete.Mechanically treated bars of grade Fe 500D or more.
| Footing -90kg/cum | 1 | 22.932 | 90 |  |  | 2063.88 | KG
| Abutment-90kg/cum | 1 | 18.963 | 90 |  |  | 1706.67 | KG
| Bed Block - 120kg/cum | 1 | 2.079 | 120 |  |  | 249.48 | KG
| Kerb -90kg/cum | 1 | 1.0908 | 90 |  |  | 98.172 | KG
| Handrail Post - 80kg/cum | 1 | 0.36 | 80 |  |  | 28.8 | KG
| Retainingwall - 110 kg/cum | 1 | 4.0748 | 110 |  |  | 448.2324 | KG
| Beam - 130kg/cm | 1 | 5.5853 | 130 |  |  | 726.0825 | KG
| Slab -110kg/cum | 1 | 5.5853 | 110 |  |  | 614.3775 | KG
| Approach Slab - 90kg/cum | 1 | 4.7805 | 90 |  |  | 430.245 | KG
| Wearing Coat Concrete - 70kg/cum | 1 | 7.237 | 70 |  |  | 506.59 | KG
| Total | [5 empty] | 6872.5294 | KG
| Total quantity | [5 empty] | 6872.5294 | KG
11 | Cement concrete lining for canal 1:2:4 finished with a floated coat of neat cement , including cement slurry etc using 20mm nominal size stone aggrerates.
| canal lining sides | 2 | 2.19 | 6.7 | 0.1 |  | 2.9346 | M3
| canal lining bottom | 1 | 4.12 | 6.7 | 0.1 |  | 2.7604 | M3
| additional area on the southern side | 2 | 2.19 | 6 | 0.1 |  | 2.628 | M3
| Total | [5 empty] | 8.323 | M3
| Total quantity | [5 empty] | 8.323 | M3
12 | Providing handrails on sides using 14 Gauge GI pipes Epoxy Primed and Painted
| Handrail | 1 | 24.24 |  |  |  | 24.24 | M
| Total | [5 empty] | 24.24 | M
| Total quantity in RM | [5 empty] | 24.24 | M
13 | 12mm thick plaster finished with a floated coat of neat cement of mix 1:3
| Slab bottom + beam bottom | 1 | 6 | 6.3 |  |  | 37.8 | M2
| Beam side | 2 | 1.4 | 6.3 |  |  | 17.64 | M2
| Beam Side | 1 | 1.1 | 6.3 |  |  | 6.93 | M2
| Retaining wall side | 1 | 9.9 | 2.058 |  |  | 20.3742 | M2
| kerb top + side | 1 | 24.24 | 0.45 |  |  | 10.908 | M2
| handrail post | 16 | 0.6 | 1 |  |  | 9.6 | M2
| Total | [5 empty] | 103.2522 | M2
| Total quantity in M2 | [5 empty] | 103.2522 | M2

## ABSTRACT
ABSTRACT ESTIMATE
CONSTRUCTION OF BRIDGE ACROSS PERIYAR VALLEY PARAVOOR BRANCH CANAL FOR UC COLLEGE,ALUVA
Sl.NO. | Specification | Quantity | Unit | Rate | Amount
1 | Demolishing the existing Cement Concrete layer on the sides manually/by mechanical means, including disposal of material within 50 metres lead as per the direction of engineer -in charge.
| Net Total(cum) | 6.5556 | M3 |  | 0
2 | Earthwork excavation by mechanical means(hydraulic excavator )/manual means for abutment construction upto 3.60m depth including disposal of excavated earth , lead upto 50m and lift upto 3.60m, disposed earth to be levelled and neatly dressed , all kinds of soil and waste.
| Net Total(cum) | 94.068 | M3 |  | 0
3 | Random Rubble in Cement Mortar
| Net Total(cum) | 5.226 | M3 |  | 0
4a | Random Rubble - Dry packed
| Net Total(cum) | 6.615 | M3 |  | 0
4b | 20cm Block Work masnory in CM
| Net Total(cum) | 6.615 | M3 |  | 0
5 | Plain Cement concrete lining for canal 1:2:4 finished with a floated coat of neat cement , including cement slurry etc using 20mm nominal size stone aggrerates.
| Net Total(cum) | 4.081 | M3 |  | 0
6 | Providing and laying in position of vibraed RCC M25 mis using 20mm nominal size coarse aggregates including shuttering and centering works,propping ,removal of formwork for foundations and footings
| Net Total(cum) | 49.4996 | M3 |  | 0
7 | Providing and laying in position of Vibrated RCC mix M25 using 20mm nominal size coarse aggregates, including shuttering & centring works, propping, and removal of formwork for slab.
| Net Total(cum) | 14.1154 | M3 |  | 0
8 | Providing and laying in position of Vibrated RCC mix M25 using 20mm nominal size coarse aggregates, including shuttering & centring works, propping, and removal of formwork for Approach slab.
| Net Total(cum) | 4.7805 | M3 |  | 0
9 | Providing and laying in position of vibrated RCC mix M25 using 20mm nominal size coarse aggregates laid in slope towards sides above the slab in a maximum size of 3x3 m grid.
| Net Total(cum) | 7.237 | M3 |  | 0
10 | Steel reinforcement for RCC work including straightening,cutting, bending,placing in position and binding all complete.Mechanically treated bars of grade Fe 500D or more.
| Net Total(cum) | 6872.5294 | KG |  | 0
11 | Cement concrete lining for canal 1:2:4 finished with a floated coat of neat cement , including cement slurry etc using 20mm nominal size stone aggrerates.
| Net Total(cum) | 8.323 | M3 |  | 0
12 | Providing handrails on sides using 14 Gauge GI pipes Epoxy Primed and Painted
| Net Total(Rm) | 24.24 | RM |  | 0
13 | 12mm thick plaster finished with a floated coat of neat cement of mix 1:3
| Net Total(cum) | 103.2522 | SQM |  | 0
| HEADING TOTAL(Rs.) |  |  |  | 0
14 | Extra charge
| Privisioin for GST |  |  | 18% | 0
ROUNDOFF
TOTAL |  |  |  |  | 0